## History
Acer DT BIOS Phase-In Checklist (Only use in MP stage)
Change History:
Date | Revision | History | Reason | Author
2008-01-22 | 1 | 1. First Release 2. Function test sku: each sku X1 3. Stress test sku: each sku X2 (Total at least 4 units) 4. Set testing cycles of suspend / reboot to 500 cycles in BIOS regression. (But still keep first MP BIOS cycles time to 1000 cycles.) | Acer Internal discuss (DQM/PM/BIOS) | DQM / Marx Hung
2008-01-31 | 1.1 | 1. Add Acer Test tool in BIOS function test and eRecovery test. 2. Mark un-necessary test item as gray (Discuss with BIOS RD) | Discuss with Foxconn | DQM / Marx Hung
2008-06-04 | 1.2 | 1. For Stress test, Vista and XP use same rule for testing (sample requirement.) 2. Update stress test sample rule : Need to use different 4 skus for testing. (min. sku : 4, each sku X1) 3. Use default power management setting to do stress test ( Hybrid sleep : ON) | Lesson learn, discuss with Foxconn | DQM / Marx Hung
2008-12-30 | 1.21 | 1. update MP BIOS Checklist 2. Attach Acer BIOS Setup and SMBIOS check list (template) | Acer BIOS RD internal update | BIOS / Yansan Tsai
2009-01-05 | 1.22 | 1. Modify some items in MP BIOS Checklist worksheet 2. Update attach file (Acer BIOS Setup Spec v1.51(template).xls) (Acer SMBIOS Spec v1.31(template).xls) | Acer BIOS RD internal update | BIOS / Yansan Tsai
2009-01-07 | 1.23 | 1. Modify "Stress Test" criteria | Acer BIOS RD internal update | BIOS / Yansan Tsai
2009-01-07 | 1.24 | 1. Update items of "BIOS Function Test" in "MP BIOS Checklist" worksheet 2. Update criteria of "Stress Test" in "MP BIOS Checklist" worksheet | Acer RD/PM internal update | BIOS / Yansan Tsai
2009-07-08 | 1.25 | 1. Update LED Definition to v1.4 2. Update Int15hAutoTest to v1.0.5.17 3. Change "flgstate.exe" to "Int15h.exe" 4. Add Windows 7 support 5. WMIAutoTest DT v3.0.0.3 6. Update attach file (Acer BIOS Setup Spec v1.53(template).xls) 7. Update SMBIOS check list to v1.33 8. add INT15h Cklt v1.1 (Consumer) validation sheet 9. add INT15h Cklt v1.1 (Commercial) validation sheet 10. Add WMI validation sheet 11. Update "Wake Up event" sheet 12. Update "Share Memory Status" table 13. Update "Test Configuration" | 1. BIOS test tool modify 2. Acer BIOS RD internal update | BIOS / Yansan Tsai
2009-09-10 | 1.26 | 1. Update eRecovery report requirement in MP BIOS Checklist sheet 2. Add Project Independent Features in MP BIOS Checklist sheet 3. Update SMBIOS check list to v1.33 r0.41 in MP BIOS Checklist sheet 4. Update validation system of Acer Boot Time Requirement sheet 5. Add "Remark" column in INT15h Cklt v1.1 (Consumer) & (Commercial) sheet 6. Add "Deep Power Off Mode" Enabled/Disabed in wake up event sheet 7. Correct Stress system number to 8 systems (2pcs/sku) in Test Configuration sheet | Acer BIOS RD internal update | BIOS / Yansan Tsai
2010-02-11 | 1.27 | 1. Revised MDA from 2009 to 2010 2. Reduce function validation for 2nd OS & Brand (in pink background) 3. Update BIOS Setup check list template in "Attached files" 4. Add BIOS Time in "Acer Boot Time Requirement" 5. Revise "Wake Up event" table and notes 6. Revise notes of LAN LED report 7. Add notes for "Share Memory Status" report | Regular update | BIOS / Yansan Tsai
2011-01-06 | 1.28 | 1. Add reviewer column 2. Added "DT Performance" on "MDA 2011" 3. Update WMI test tool to v4.1.0.2 4. Added "Audio four-part ID" check item 5. Modified stress test criteria 6. Update BIOS Setup check list template in "Attached files" 7. Revised the SMBIOS/DMI check list to r0.42 in "Attached files" 8. Modified "DT Performance" worksheet 9. Modified "Wake Up event" worksheet 10. Modified and added "LED Definition v1.4" Specification on "LAN LED" worksheet 11. Modify criteria for 2nd OS & Brand (in pink background) | Regular update | BIOS / Yansan Tsai

## MP BIOS Checklist
[Project Name] BIOS Phase In Check List
Model Name |  | BIOS Version / Size(MB) / Date |  | Test Start Date | Test Finish Date | Report Date |  | Tester |  |  |  | Reviewer
RCD Version
Item | Test Item Description |  |  |  |  | Report Status |  | Remark
[6 empty] | SYS 1 | SYS 2
1 | MDA2011 |  | S3 validation with pwrtest.exe |  |  |  |  | PWRTEST
|  |  | BIOS implement need to meet "DT Performance" |  |  |  |  | v1.3d
2 | Acer Boot requirement |  | Please refer "Acer Boot Time Requirement" sheet
3 | RCD Installation Test |  | Install RCD (In detail) a. Check the RCD Boot; b.RCD Install well; c. Check BIOS interface (NAPP7.0)
4 | BIOS Function Test |  | BIOS Flash Test (FreeDOS mode and Win mode)(UEFI Flash tool) |  |  |  |  | 5 times per SKU (EVT/DVT/MP)
Bootblock function verify (FDD/CD-ROM/DVD-ROM/USB storage)
|  |  | BIOS Item Check |  |  |  |  | check attach file 1. Go full validation if modified.
|  |  | DMI Table Check |  |  |  |  | check attach file 2. Go full validation if modified.
Acer Property check (Copyright)
Acer Multi-Brand BIOS validation a. Logo; b. SMBIOS: Type0-3
|  |  | Buzzer Function Check |  |  |  |  | Go full validation if modified.
|  |  | Function Key Check |  |  |  |  | ref. Multi-Brand Table (ODM). Go full validation if modified.
|  |  | Muti-Boot Menu Sequence Test |  |  |  |  | Go full validation if modified.
|  |  | UMA Share Memory setting test |  |  |  |  | Go full validation if modified.
Special feature test refer to POR
|  |  | Smart Fan Function Test after resume from S3/S4/S5. (5 times)(per chassis) |  |  |  |  | reduce for 2nd OS or Brand if using same thermal poliicy
5 | Power Management Test |  | ACPI Wake Up Event Function Test
|  |  | LED Check |  |  |  |  | LED Definition v1.4. Go full validation if modified.
6 | Recovery Check |  | Int15AutoTest.exe (Windows Auto Test) (report with snapshot and log file) |  |  |  |  | Int15hAutoTest v1.0.5.17
|  |  | Int15h.exe (DOS, Manual Test) |  |  |  |  | v1.0. Go full validation if modified.
|  |  | WMIAutoTest (report with snapshot and log file) |  |  |  |  | WMIAutoTest DT v4.1.0.2
7 | Windows 7 support |  | SLP KEY change to 2.1 if it's 2.0
USB ASL for WIN7
Change verb table for WHQL– remove internal speaker function if no support
BIOS version (start from P01-A0)
For DMI info checking, please take care the family string in SMBIOS type 1, offset 1Ah
8 | Project Independent Features support |  | BIOS ROM ID (It's unique) (Please list ROM ID) |  |  |  |  | Usage: AFUDOS /S (First 5 characters)
Storage SATA mode (Please list the default setting, sync with Setup)
|  |  | System SSID (Please list the SSID value with hexadacimal mode) |  |  |  |  | Provide BIOS Spec for Multi-Brand (latest version)
|  |  | Audio four-part ID (SVID_SSID_HDAID) |  |  |  |  | Check "Acer Desktop Audio spec" latest version
9 | Bugs Fixed and Changes (Base on release note)
[6 empty] | SYS 1 | SYS 2 | SYS 3 | SYS 4 | SYS 5 | SYS 6 | SYS 7 | SYS 8 | Remark
10 | Stress Test (For Regression & 2nd OS go 50% criteria) |  | Suspend(S3/S4) : 500 times (Coverage : Onboard/Add-on VGA) 500 times w/o error. (Acer Suspend Tool)
Reboot test : 500 times (Coverage : Onboard/Add-on VGA) 500 times w/o error. (Acer Reboot Tool)
Heavy load test DVT SKU 8 hours no error (1) LAN←→HDD, HDD←→HDD, ODD→HDD. (2) TWO HDD + TWO ODD Stress test (Copy & Compare files)
|  |  | USB 2.0/3.0(4 devices) / IEEE1394 / e-SATA data transfer overnight test Use Acer AVLC components: (1). Highest CPU & frequency. (2). Highest VGA card. (3). Full of double sides memory (as: 2GBx4/x2 or 1GBx4/x2) DVT SKU 8 hours no error | [10 empty] | Remove for Founder
Intel MaxPower 85%-100% (or AMD ThermNow 100%) with all type CPU DVT SKU 12 hours no error
Play DVD/BD + 7-zip benchmark mode DVT SKU 12 hours no error(Depends on different SKU, play BD only in BD skus)
3DMark06 Benchmark + HDD tune & Demo mode run (Monitor HDD Temperature not over 60℃) DVT SKU 12 hours no error
|  |  | Game Stress: Display resolution must above 1280x1024(4:3) or 1440x900(16:10) or 1440x900(16:9) Run these game over 8 hours & no error. (Test failed in 4 hours: Severity 1, test failed in 4~8 hours: Severity 2) | [10 empty] | Remove for Founder
Memory test (Coverage : Onboard/Add-on VGA) DVT SKU 12 hours no error. (Windows Memory Diagnostics Tool & memtest)
No. | Bug Description |  |  |  |  | SYS 3: Remark (Bug ID/Action)
1
2
3
4
5
Attached files: |  |  | Note
1 |  |  | 1
2 |  |  | 2
Note | bar: SYS 1 to SYS 2
1 | For 2nd OS & Brand verify, update "Product Information" with attached "Acer BIOS Setup check list".
2 | For 2nd OS & Brand verify, update "Type 0, 1, 2, 3" information with attached "Acer SMBIOS check list".

## Share Memory Status
Share Memory Status
Project Name
BIOS Version
RCD Version
Share Memory report
System Memory | BIOS setting |  | VGA memory under XP/Vista/Windows7 |  |  |  | System Memory | BIOS setting |  | VGA memory under XP/Vista/Windows7
| UMA Frame Buffer | Post Show | Total Available Graplics memory | Dedicated Video Memory | System Video Memory | Shared System Memory |  | UMA Frame Buffer | Post Show | Total Available Graplics memory | Dedicated Video Memory | System Video Memory | Shared System Memory
8G (If POR support) | 32MB | [5 empty] | 16G (If POR support) | 32MB
| 64MB | [6 empty] | 64MB
| 128MB | [6 empty] | 128MB
| 256MB | [6 empty] | 256MB
| Auto | [6 empty] | Auto
6G (If POR support) | 32MB | [5 empty] | 14G (If POR support) | 32MB
| 64MB | [6 empty] | 64MB
| 128MB | [6 empty] | 128MB
| 256MB | [6 empty] | 256MB
| Auto | [6 empty] | Auto
4G | 32MB | [5 empty] | 12G | 32MB
| 64MB | [6 empty] | 64MB
| 128MB | [6 empty] | 128MB
| 256MB | [6 empty] | 256MB
| Auto | [6 empty] | Auto
3G | 32MB | [5 empty] | 10G | 32MB
| 64MB | [6 empty] | 64MB
| 128MB | [6 empty] | 128MB
| 256MB | [6 empty] | 256MB
| Auto | [6 empty] | Auto
2G | 32MB | [5 empty] | 9G | 32MB
| 64MB | [6 empty] | 64MB
| 128MB | [6 empty] | 128MB
| 256MB | [6 empty] | 256MB
| Auto | [6 empty] | Auto
1G | 32MB | [5 empty] | 8G | 32MB
| 64MB | [6 empty] | 64MB
| 128MB | [6 empty] | 128MB
| 256MB | [6 empty] | 256MB
| Auto | [6 empty] | Auto
Notes
1. Fozen the data in first MP BIOS, and for update version, just check if there are any problem.
2. Remark if there is any Spec or design limitation